## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a Developer, I want to upload or paste Python code so that the system can accept it for analysis | MUST HAVE | None | Ishika Patidar | 3- Completed
Sprint 2 | Sprint 2 | US-02 | As a Developer, I want syntax errors and undefined variables to be detected automatically | MUST HAVE | US-01 | Ishika Patidar | 3- Completed
Sprint 3 | Sprint 3 | US-03 | As a Developer, I want my code to be checked against PEP8 standards for better coding practices | MUST HAVE | US-02 | Ishika Patidar | 3- Completed
Sprint 3 | Sprint 3 | US-04 | As a Developer, I want to securely store API keys using environment variables to protect sensitive data | SHOULD HAVE | US-03 | Ishika Patidar | 3- Completed
Sprint 4 | Sprint 4 | US-05 | As a Developer, I want to see before-and-after code snippets for better understanding | SHOULD HAVE | US-04 | Ishika Patidar | 3- Completed
Sprint 4 | Sprint 4 | US-06 | As a Developer, I want AI-based suggestions for improving code quality | SHOULD HAVE | US-05 | Ishika Patidar | 3- Completed
Sprint 4 | Sprint 4 | US-07 | As a Developer, I want clear explanations of errors so that I can understand and fix them easily | MUST HAVE | US-06 | Ishika Patidar | 3- Completed
Sprint 5 | Sprint 5 | US-08 | As a Developer, I want time and space complexity analysis so that I can optimize my code performance | MUST HAVE | US-07 | Ishika Patidar | 3- Completed
Sprint 5 | Sprint 5 | US-09 | As a Developer, I want suggestions for improving code readability and structure | SHOULD HAVE | US-08 | Ishika Patidar | 3- Completed
Sprint 6 | Sprint 6 | US-10 | As a Developer, I want a user-friendly interface with input and output sections for better interaction | MUST HAVE | US-09 | Ishika Patidar | 3- Completed
Sprint 6 | Sprint 6 | US-11 | As a Developer, I want integration with Groq API so that the system can generate fast AI responses | MUST HAVE | US-10 | Ishika Patidar | 3- Completed
Sprint 7 | Sprint 7 | US-12 | As a Developer, I have learned a new framework called reflex which is a extended framework of react and this framework gives us the felxibility to develop the backend in python. | MUST HAVE | US-11 | Ishika Patidar | 3- Completed
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Analyze project requirements and workflow for AI-driven code reviewer | 2025-12-04 | 2025-12-05 | Your Name | Design | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Accept Python code input via paste/upload functionality | 2025-12-08 | 2025-12-11 | Your Name | Build | 3- Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9/15/2016 or 15-Sep-2016
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9/15/2016 or 15-Sep-2016
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is the total task estimated in hours for all the user stories
Note on J3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 1 work
Note on K3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 2 work
Note on L3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 3 work
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 4 work
Note on N3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 5 work
Note on O3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 6 work
Note on P3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 7 work
Note on Q3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 8 work
Note on R3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 9 work
Note on S3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 10 work
Note on T3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 11 work
Note on U3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 12 work
Note on V3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 13 work
Note on W3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | None | Analyzed project requirements and explored AST-based code parsing approach
Sprint 1 | Day 2 | Difficulty understanding AST node traversal for Python code | Reviewed Python AST documentation and tested sample code parsing
Sprint 1 | Day 3 | Handling unused imports and unreachable code detection | Implemented rule-based checks using AST and validated with sample programs
Sprint 1 | Day 4 | PEP8 style violations not detected consistently | Integrated PEP8 guidelines and improved style-checking logic
Sprint 1 | Day 5 | Difficulty in identifying a suitable model for code analysis and optimization tasks | Identified and integrated the Qwen model from Hugging Face for improved coding-related suggestions

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-12-01 | 2025-12-14 | Your name | Better planning | Last-minute coding | Daily testing | Follow sprint plan
2
3
4
5
6
7